## Foglio1
| semster 1 | [5 empty] | semester 2 | [5 empty] | semester 3 | [5 empty] | semester 4
ACTIVITIES | 2026-02-01 | 2026-03-01 | 2026-04-01 | 2026-05-01 | 2026-06-01 | 2026-07-01 | 2026-08-01 | 2026-09-01 | 2026-10-01 | 2026-11-01 | 2026-12-01 | 2027-01-01 | 2027-02-01 | 2027-03-01 | 2027-04-01 | 2027-05-01 | 2027-06-01 | 2027-07-01 | 2027-08-01 | 2027-09-01 | 2027-10-01 | 2027-11-01 | 2027-12-01 | 2028-01-01
WP1 Mapping of SMEs, skills analysis and development of Training Strategy
Act.1.1 Identification of SMEs in key manufacturing sectors.
D1.1.1 Standardized Template for the mapping of SMEs | bar: 2026-04-01
D1.1.2 Initial Report | bar: 2026-05-01 to 2026-07-01
Act.1.2 Analysis of required skills
D1.2.1 Questionnaire for SMEs | bar: 2026-06-01 to 2026-07-01
D1.2.2 Final Report | bar: 2026-08-01 to 2027-01-01
Act.1.3 Identification of training needs in secondary schools
D1.3.1 Template to analyze curricula | bar: 2026-06-01 to 2026-07-01
D1.3.2 Comprehensive Report | bar: 2026-08-01 to 2027-01-01
Act.1.4 Development of a training strategy | bar: 2027-03-01
D1.4.1 Training Strategy | bar: 2027-01-01 to 2027-03-01
D1.4.2 Final Co- Creation Workshop Report | bar: 2027-03-01 to 2027-07-01
WP2 Innovation in education and training through collaboration
Act. 2.1 Creation of a Learning Management System.
D2.2.1 Learning Management System | bar: 2027-02-01 to 2027-06-01
D2.2.2 Events Reports | bar: 2027-04-01 to 2027-07-01
Act. 2.2 Content Design for AR/VR Headsets
D2.2.1 Skills Development Framework | bar: 2027-02-01 to 2027-04-01
D2.2.2 Prototype AR/VR Demo | bar: 2027-04-01 to 2027-07-01
Act. 2.3 Collaborative Workshop
D2.3.1 Signing MoU to continue transnational collaboration over project end. | 2027-10-01: workshop in PL
Act. 2.4 Piloting of training programmes
D2.4.1 Guidelines for School Selection | bar: 2027-04-01 to 2027-07-01
D2.4.2 Package of developed solutions | bar: 2027-09-01 to 2028-01-01
D2.4.3 Intermediate report on the pilot implementation | bar: 2027-09-01
D2.4.4 Final Report on the pilot implementation | bar: 2027-10-01 to 2027-11-01
Act.2.5 Sharing of results
D2.5.1 Local Event Reports | 2027-10-01: 3 local events
D2.5.2 Regional conference Report | 2027-12-01: 1 FC in IT
Communication activities (web site,social media, newsletter)
Project management and reporting | 2026-09-01: PR1; 2027-03-01: PR2; 2027-04-01: MR; 2027-09-01: PR3 | FR
Effective engagement of SMEs - D.1.2.2
Draft of the pilot implementation (extra report)
Final report on the pilot D2.4.4. Final report on the pilot implementation
M1
M2
M3